## Detailed Plan
Phase | Step | Task | Details | RACI (R/A/C/I) | Timeline (Days) | Risk | Mitigation | Automation
Pre-Requisite | 1 | Inventory Assessment | Data size, users, permissions | Infra Team / Manager / App Team / Stakeholders | 2 | Incomplete data info | Use discovery tools | Manual + scripts
Pre-Requisite | 2 | Network Assessment | Bandwidth & latency | Network Team / Manager / Infra / Stakeholders | 2 | Low bandwidth | Plan offline transfer | N/A
Pre-Requisite | 3 | Access Review | NTFS & AD mapping | AD Team / Manager / Infra / Security | 2 | Permission mismatch | Export ACLs | PowerShell
Pre-Requisite | 4 | Choose Target | Decide FSx / S3 / EC2 File Server |  | 2
Pre-Requisite | 5 | AWS Setup | Account, IAM, VPC | Cloud Team / Manager / Security / Infra | 3 | Misconfiguration | Follow landing zone | Terraform
Implementation | 6 | VPC Setup | Subnets, routing | Cloud Team / Manager / Network / Security | 2 | Network issue | Validate routing | Terraform
Implementation | 7 | Connectivity | VPN/Direct Connect | Network Team / Manager / Cloud / Infra | 3 | Connectivity failure | Redundant VPN | Terraform
Implementation | 8 | Directory Setup | AD integration | AD Team / Manager / Cloud / Security | 2 | Auth failure | Test join | Automation scripts
Implementation | 9 | FSx Setup | Provision FSx | Cloud Team / Manager / Infra / Security | 2 | Wrong sizing | Right capacity planning | Terraform
Implementation | 10 | DataSync Setup | Agent & config | Cloud Team / Manager / Infra / Security | 2 | Agent failure | Reinstall agent | Automation scripts
Implementation | 11 | Configure DataSync | Create source & destination locations |  | 3
Implementation | 12 | Initial Sync | Full data copy | Cloud Team / Manager / Infra / App | 3 | Data loss | Checksum validation | AWS DataSync
Implementation | 13 | Incremental Sync | Delta sync | Cloud Team / Manager / Infra / App | 3 | Sync lag | Schedule frequent sync | AWS DataSync
Validation | 14 | Data Validation | File count & size | QA / Manager / Infra / Users | 2 | Mismatch | Re-sync | Scripts
Validation | 15 | Permission Check | ACL validation | AD Team / Manager / Infra / Security | 2 | Access issues | Fix ACL | PowerShell
Validation | 16 | User Testing | User access | Users / Manager / Infra / App | 2 | User issues | Rollback plan | Manual
Validation | 17 | App Testing | Dependent apps | App Team / Manager / Infra / Users | 2 | App failure | Fallback plan | Manual
Cutover | 18 | Freeze Changes | Stop writes | Infra / Manager / Users / App | 1 | Data inconsistency | Announce downtime | Manual
Cutover | 19 | Final Sync | Last sync | Cloud / Manager / Infra / App | 1 | Missed data | Verify logs | AWS DataSync
Cutover | 20 | DNS Update | Switch shares | Network / Manager / Infra / Users | 1 | DNS delay | Lower TTL | Scripts
Cutover | 21 | User Redirection | Point to AWS | Infra / Manager / Users / App | 1 | User confusion | Communication plan | GPO
Post | 22 | Monitoring | Enable logs | Cloud / Manager / Infra / Security | 2 | No visibility | CloudWatch alerts | Terraform
Post | 23 | Backup | Enable backup | Cloud / Manager / Infra / Security | 2 | Data loss | Backup policy | AWS Backup
Post | 24 | Security | Encryption & IAM | Security / Manager / Cloud / Infra | 2 | Breach risk | Enable KMS | Terraform
Post | 25 | Cost Optimization | Storage tuning | Cloud / Manager / Finance / Infra | 2 | High cost | Lifecycle policy | Automation
Post | 26 | Decommission | Shutdown on-prem | Infra / Manager / Users / App | 2 | Premature shutdown | Final validation | Manual